## Project Info
Field | Value
Project Name | OpenCart BookStore (E-Commerce Demo)
Client | OpenCart
Website Under Test (WUT) | https://demo.opencart.com/
Test Type | Manual Functional + UI + Regression
Test Levels | Component, Integration, System, UAT (mock)
Created By | QA Team (You)
Attendees | Scrum Team
Creation Date | 14-08-2025
Approval Date

## Product Backlog
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria
BS_Epic_001 | US001 | Registration | As a new visitor, I want to register so I can create an account. | New | User can register with valid data; validation errors for invalid input; email unique.
BS_Epic_001 | US002 | Login | As a registered user, I want to log in so I can access my account. | New | Valid credentials allow login; invalid show error; remember-me optional.
BS_Epic_001 | US003 | Profile Update | As a logged-in user, I want to update my profile to keep information current. | New | Profile changes saved and visible on next login.
BS_Epic_002 | US004 | Search Books | As a user, I want to search books by keyword so I can find items fast. | New | Relevant results for keyword; no-result message when none.
BS_Epic_002 | US005 | Browse Categories | As a user, I want to browse categories so I can explore books. | New | Correct category listing and pagination.
BS_Epic_002 | US006 | Filter & Sort | As a user, I want to filter and sort results to narrow choices. | New | Filter and sort change result set and order accordingly.
BS_Epic_003 | US007 | Add to Cart | As a user, I want to add books to the cart. | New | Item appears in cart with price/qty; mini-cart updates count.
BS_Epic_003 | US008 | Update/Remove Cart | As a user, I want to change qty or remove items from cart. | New | Qty updates totals; remove deletes item; cannot set negative qty.
BS_Epic_004 | US009 | Guest Checkout | As a user, I want to place an order as guest. | New | Guest flow collects shipping/payment and completes order.
BS_Epic_004 | US010 | Payment Gateway | As a user, I want to pay using card/COD (demo). | New | Payment processed; order confirmation displayed + email.
BS_Epic_005 | US011 | Order History | As a user, I want to view order history and details. | New | Orders listed with status, totals, and downloadable invoice.
BS_Epic_006 | US012 | Wishlist | As a user, I want to save items to wishlist. | New | Add/Remove wishlist; persist across sessions.
BS_Epic_006 | US013 | Compare | As a user, I want to compare products. | New | Compare table shows attributes side by side.
BS_Epic_007 | US014 | Write Review | As a user, I want to review a product. | New | Submit review with rating and comment; validation enforced.
BS_Epic_008 | US015 | Apply Coupon | As a user, I want to apply a coupon on cart. | New | Valid coupon discounts totals; invalid shows error.
BS_Epic_009 | US016 | Address Book | As a user, I want to manage addresses for shipping. | New | Add/Edit/Delete addresses; set default address.
BS_Epic_010 | US017 | Return Request | As a user, I want to request a return. | New | RMA form submitted; confirmation email sent.
BS_Epic_011 | US018 | Email Notifications | As a user, I want emails for order events. | New | Emails sent for registration, order confirmation, shipment.
BS_Epic_012 | US019 | Admin Add Product | As an admin, I want to add products to catalog. | New | New product appears on storefront with correct data.
BS_Epic_012 | US020 | Admin Manage Stock | As an admin, I want to update stock and price. | New | Stock/price updates reflected on product and cart.

## Sprint Planning
User Story ID | Feature | Story Points | Sprint
US001 | Registration | 8 | 1
US002 | Login | 5 | 1
US003 | Profile Update | 3 | 2
US004 | Search Books | 5 | 2
US005 | Browse Categories | 3 | 2
US006 | Filter & Sort | 5 | 3
US007 | Add to Cart | 5 | 3
US008 | Update/Remove Cart | 3 | 3
US009 | Guest Checkout | 8 | 4
US010 | Payment Gateway | 8 | 4
US011 | Order History | 3 | 5
US012 | Wishlist | 3 | 5
US013 | Compare | 3 | 5
US014 | Write Review | 3 | 6
US015 | Apply Coupon | 5 | 6
US016 | Address Book | 5 | 6
US017 | Return Request | 5 | 7
US018 | Email Notifications | 3 | 7
US019 | Admin Add Product | 8 | 8
US020 | Admin Manage Stock | 5 | 8

## Tasks
Developer Tasks | QA Tasks
Understand Requirements | Understand Requirements
Design | Write Test Scenarios
Coding | Write Test Cases
Unit Testing | Test Case Review
Integration Testing | Test Data Preparation
Code Review | Test Execution
Bug Fixes | Retest & Regression
Team Meetings | Team Meetings
Any Other | Test Closure

## Test Cases
Test Case ID | Epic | User Story ID | Title | Pre-Conditions | Test Steps | Expected Result | Actual Result | Status | Severity | Priority | Executed By | Execution Date
TC001 | BS_Epic_001 | US001 | Register with valid data | Logged-out user unless specified | Open site > My Account > Register > Fill all valid fields > Continue | Account created and success message shown; redirected to account page | Account created; success banner displayed | Pass | Low | P3 | QA | 14-08-2025
TC002 | BS_Epic_001 | US001 | Register with existing email | Logged-out user unless specified | Register with an email already used | Error shown: E-Mail Address is already registered! | Proper error displayed and registration blocked | Pass | Medium | P2 | QA | 14-08-2025
TC003 | BS_Epic_001 | US001 | Register with invalid email | Logged-out user unless specified | Enter invalid email format and submit | Client-side or server-side validation blocks submission | Form allowed submit without specific email format error | Fail | High | P1 | QA | 14-08-2025
TC004 | BS_Epic_001 | US001 | Mandatory field validation | Logged-out user unless specified | Leave mandatory fields blank and submit | Errors highlighting required fields | Required field errors shown | Pass | Medium | P3 | QA | 14-08-2025
TC005 | BS_Epic_001 | US001 | Password min length check | Logged-out user unless specified | Enter short password and submit | Validation error for minimum password length | Error shown: Password must be between 4 and 20 characters! | Pass | Medium | P3 | QA | 14-08-2025
TC006 | BS_Epic_001 | US001 | Privacy policy checkbox | Logged-out user unless specified | Do not accept privacy policy and submit | Error requiring privacy policy agreement | Warning displayed preventing registration | Pass | Medium | P3 | QA | 14-08-2025
TC007 | BS_Epic_001 | US002 | Login with valid credentials | Logged-out user unless specified | My Account > Login > enter valid email + password > Login | Dashboard is displayed; My Account shows user name | Logged in successfully | Pass | Medium | P2 | QA | 14-08-2025
TC008 | BS_Epic_001 | US002 | Login with invalid credentials | Logged-out user unless specified | Enter wrong password and submit | Warning: No match for E-Mail Address and/or Password. | Correct warning displayed; stays on login page | Pass | Medium | P3 | QA | 14-08-2025
TC009 | BS_Epic_001 | US002 | Logout | Logged-out user unless specified | After login click My Account > Logout | Logout success page and session cleared | Logout success page displayed | Pass | Medium | P3 | QA | 14-08-2025
TC010 | BS_Epic_001 | US003 | Update profile - telephone | Logged-out user unless specified | Login > Edit Account > change telephone > Continue | Profile updated success message | Success: Your account has been successfully updated. | Pass | Medium | P3 | QA | 14-08-2025
TC011 | BS_Epic_002 | US004 | Search by keyword returns results | Logged-out user unless specified | Enter 'Mac' in search > Search | Products relevant to 'Mac' listed | Multiple Mac products listed | Pass | Medium | P3 | QA | 14-08-2025
TC012 | BS_Epic_002 | US004 | Search no results | Logged-out user unless specified | Enter rare keyword > Search | Shows 'There is no product that matches the search criteria.' | No results message displayed | Pass | Medium | P3 | QA | 14-08-2025
TC013 | BS_Epic_002 | US005 | Browse category navigation | Logged-out user unless specified | Desktops > Mac | Category page loads with products and breadcrumb | Category page loaded correctly | Pass | Medium | P3 | QA | 14-08-2025
TC014 | BS_Epic_002 | US006 | Filter by price | Logged-out user unless specified | Use any available filter/sort by Price (High > Low) | Product order changes accordingly | Order changed; highest price first | Pass | Medium | P3 | QA | 14-08-2025
TC015 | BS_Epic_002 | US006 | Sort by Name A-Z | Logged-out user unless specified | Sort by Name (A - Z) | Products sorted alphabetically | Observed alphabetical order | Pass | Medium | P3 | QA | 14-08-2025
TC016 | BS_Epic_002 | US006 | Pagination works | Logged-out user unless specified | Go to page 2 on category results | Next page loads with products | Page 2 loaded with items | Pass | Medium | P3 | QA | 14-08-2025
TC017 | BS_Epic_003 | US007 | Add item to cart from product page | Logged-out user unless specified | Open product > Add to Cart | Success message; cart count increases; item visible in cart | Success banner displayed; cart shows item | Pass | Medium | P3 | QA | 14-08-2025
TC018 | BS_Epic_003 | US007 | Add item to cart from listing | Logged-out user unless specified | From listing click Add to Cart | Item added; count update | Item added and count updated | Pass | Medium | P3 | QA | 14-08-2025
TC019 | BS_Epic_003 | US008 | Update qty in cart | Logged-out user unless specified | Open cart > change quantity > Update | Totals reflect new qty | Totals updated correctly | Pass | Medium | P3 | QA | 14-08-2025
TC020 | BS_Epic_003 | US008 | Remove item from cart | Logged-out user unless specified | Open cart > Remove | Item removed; totals updated to zero if last item | Item removed successfully | Pass | Medium | P3 | QA | 14-08-2025
TC021 | BS_Epic_003 | US007 | Add out-of-stock item (if any) | Logged-out user unless specified | Try adding an out-of-stock item | Should prevent adding or show out of stock | No clear message; allowed to add with 0 stock | Fail | Medium | P2 | QA | 14-08-2025
TC022 | BS_Epic_004 | US009 | Guest checkout flow | Logged-out user unless specified | Add item > Checkout > Guest checkout > fill details > confirm | Order placed and confirmation shown | Order confirmation page displayed | Pass | High | P2 | QA | 14-08-2025
TC023 | BS_Epic_004 | US010 | Payment with demo method success | Logged-out user unless specified | Choose demo payment method (e.g., Cash on Delivery / Dummy) | Order success page shown and order ID generated | Order ID generated and shown | Pass | High | P1 | QA | 14-08-2025
TC024 | BS_Epic_004 | US010 | Invalid card details blocked (if card form present) | Logged-out user unless specified | Enter invalid card number and submit | Validation error; payment not processed | Payment page allowed proceed to next step without clear error | Fail | High | P1 | QA | 14-08-2025
TC025 | BS_Epic_004 | US009 | Required terms & conditions | Logged-out user unless specified | Do not accept T&C > try to proceed | Should block and show warning | Warning displayed preventing continue | Pass | Medium | P3 | QA | 14-08-2025
TC026 | BS_Epic_004 | US010 | Order confirmation email | Logged-out user unless specified | Place order > check email inbox (mock) | Order confirmation email received | Email received in test inbox (simulated) | Pass | Medium | P3 | QA | 14-08-2025
TC027 | BS_Epic_004 | US009 | Address validation | Logged-out user unless specified | Leave address fields blank > continue | Validation errors shown | Validation messages displayed | Pass | Medium | P3 | QA | 14-08-2025
TC028 | BS_Epic_005 | US011 | View order history | Logged-out user unless specified | Login > Order History | Order list shows previous orders | List displayed with latest order | Pass | Medium | P3 | QA | 14-08-2025
TC029 | BS_Epic_006 | US012 | Add to wishlist | Logged-out user unless specified | Product page > Add to Wishlist | Item saved to wishlist and accessible from account | Wishlist updated with item | Pass | Medium | P3 | QA | 14-08-2025
TC030 | BS_Epic_006 | US013 | Add to compare | Logged-out user unless specified | Product page > Compare this Product | Item added to comparison; compare page shows items | Compare page shows two items side by side | Pass | Medium | P3 | QA | 14-08-2025
TC031 | BS_Epic_007 | US014 | Submit review without rating | Logged-out user unless specified | Leave rating empty and submit | Should show validation error | Error displayed: Please select a review rating! | Pass | Medium | P3 | QA | 14-08-2025
TC032 | BS_Epic_007 | US014 | Submit review with valid data | Logged-out user unless specified | Provide rating/comment > submit | Review submitted (may require approval) | Message shown: Thank you for your review. It has been submitted to the webmaster for approval. | Pass | Medium | P3 | QA | 14-08-2025
TC033 | BS_Epic_008 | US015 | Apply invalid coupon | Logged-out user unless specified | Cart > Use Coupon Code > enter invalid | Error message for invalid coupon | Warning: Coupon is either invalid or expired! | Pass | Medium | P3 | QA | 14-08-2025
TC034 | BS_Epic_009 | US016 | Add new address | Logged-out user unless specified | Account > Address Book > New Address | Address saved and appears in list | Address added successfully | Pass | Medium | P3 | QA | 14-08-2025
TC035 | BS_Epic_009 | US016 | Delete address | Logged-out user unless specified | Address Book > Delete | Address removed | Address removed from list | Pass | Medium | P3 | QA | 14-08-2025
TC036 | BS_Epic_010 | US017 | Submit return request | Logged-out user unless specified | Account > Return > submit with order details | RMA created and confirmation displayed | Return request submitted confirmation shown | Pass | Medium | P3 | QA | 14-08-2025
TC037 | BS_Epic_011 | US018 | Receive registration email | Logged-out user unless specified | Register new account and check email (mock) | Registration email received | Welcome email received (simulated) | Pass | Medium | P3 | QA | 14-08-2025
TC038 | BS_Epic_012 | US019 | Admin can add product | Logged-out user unless specified | Admin login > Catalog > Products > Add New > Save | Product visible on storefront | Product created; appears in catalog (admin simulation) | Pass | Medium | P3 | QA | 14-08-2025
TC039 | BS_Epic_012 | US020 | Admin update stock reflects on storefront | Logged-out user unless specified | Admin change quantity > Save > check product page | Stock info updated | Stock change reflected after refresh | Pass | Medium | P3 | QA | 14-08-2025
TC040 | BS_Epic_008 | US015 | Apply valid coupon (if available) | Logged-out user unless specified | Enter valid demo coupon | Discount applied to totals | No demo coupon available; cannot verify | Fail | Low | P4 | QA | 14-08-2025

## Bug Report
Bug ID | Related TC | Epic | User Story ID | Summary | Severity | Priority | Environment | Steps to Reproduce | Expected Result | Actual Result | Status | Assigned To
BUG001 | TC003 | BS_Epic_001 | US001 | Registration accepts invalid email format | High | P1 | Chrome 126, Windows 11 | Register with email 'user@invalid' and submit | Validation should block and show error near email field | Form submission proceeds without format error | Open | Dev A
BUG002 | TC025 | BS_Epic_003 | US007 | Out-of-stock item can be added to cart | Medium | P2 | Chrome 126, Windows 11 | Choose an item marked out of stock; click Add to Cart | System should prevent adding OOS item or show clear message | Item added; no OOS warning | Open | Dev B
BUG003 | TC027 | BS_Epic_004 | US010 | Payment form allows proceed with invalid card details | High | P1 | Chrome 126, Windows 11 | Enter 4111111111111111 with invalid exp/CVV; click Pay | Form should block payment and show validation errors | Proceeded to next step; no validation on card | Open | Dev C
BUG004 | TC031 | BS_Epic_008 | US015 | No demo valid coupon available; UI still shows Apply field without hint | Low | P4 | Chrome 126, Windows 11 | Cart > Apply Coupon > enter 'SAVE10' (non-existent) | Either provide working demo coupon or a helper text to guide user | Generic error only; UX unclear for trainees | Open | UX
BUG005 | TC034 | BS_Epic_012 | US020 | Stock update delay on storefront (cache) | Medium | P3 | Chrome 126, Windows 11 | Admin changes stock > refresh product page immediately | Storefront should reflect stock instantly or show cache notice | Stock change reflected after delay/refresh | Open | Dev Ops
BUG006 | TC036 | BS_Epic_004 | US010 | Order confirmation page lacks clear order summary section on small viewports | Medium | P3 | Chrome 126, Windows 11 | Place order on mobile emulator 360x640; observe summary | Order summary should be readable and complete on small screens | Summary truncated; requires horizontal scroll | Open | Frontend

## Test Summary
Metric | Value
Total Test Cases | 40
Passed | 36
Failed | 4
Blocked/Not Run | 0
Execution % | 100.0%
Total Bugs Logged | 6
Severity (High/Med/Low) | H:2 M:3 L:1
Defect Density (Bugs/Test Cases) | 0.15

## Final Documentation
Section | Details
1. Scope (In) | User account, product catalog, cart, checkout, payments (demo), orders, wishlist, compare, coupons, address book, returns, notifications, basic admin catalog.
2. Scope (Out) | 3rd-party payment production validation, performance/load testing, security pen-test, real email delivery (simulated).
3. Test Environment | Windows 11, Chrome 126, Edge 126; QA data only; Demo site: https://demo.opencart.com/
4. Entry Criteria | Demo site accessible; stable build; test data prepared; user roles available.
5. Exit Criteria | >=95% critical tests pass; no open High severity defects; summary report signed off.
6. Risks/Assumptions | Demo site data can reset; features may be limited; email checks simulated.
7. Deliverables | Backlog, Sprint plan, Test cases with results, Bug report, Summary report, Closure note.
8. Team & Roles | QA: You (Manual Tester); Dev/SM/PO: Simulated for practice.
9. Schedule | 4 two-week sprints for core features; additional sprints for admin.
10. Tools | Excel, Browser DevTools, Screenshots tool.
11. Website Link | https://demo.opencart.com/
12. Conclusion | Core flows pass; known issues logged. Ready for learning/demo purposes.